## developer report (Jira) (9)
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Fix versions | Priority | Status | Reporter | Reporter Id | Resolution | Created | Updated | Due date | Custom field (Customer Name)
Bug | SHIV-1524 | 15322 | Approval Status Not Clearly Displayed in Purchase Order List After Amend Action | Somnath kumbhakar | 712020:6f36c619-c84c-4c7e-afa2-8d8976bdfd5e |  | Medium | To Do | Mohit sangwan | 712020:21fd6452-cd2e-4c89-a2d2-7ab3c0a5c6f8 |  | 2026-01-19 11:46 | 2026-01-19 11:50 | 2026-01-19 | Shivaizer
Bug | SHIV-1516 | 15313 | Receipt Voucher Amendment – Invoice amount validation issue and Invoice details not visible on View/Approval | Kuldeep yadav | 712020:074b7522-30d5-4113-b52e-0df2956b5dbc | 1.2.4.2.Q260118 | Highest | Reopen | Mohit sangwan | 712020:21fd6452-cd2e-4c89-a2d2-7ab3c0a5c6f8 |  | 2026-01-17 13:38 | 2026-01-19 14:52 | 2026-01-17 | Shivaizer
Bug | SHIV-1495 | 15282 | 400 Error occurs when clicking on Amend in Comparison module | Anshul Chandra | 6359222bd66d8108a123c4fe |  | Medium | In Progress | Mohit sangwan | 712020:21fd6452-cd2e-4c89-a2d2-7ab3c0a5c6f8 |  | 2026-01-14 17:24 | 2026-01-19 14:43 | 2026-01-17 | Shivaizer
Bug | SHIV-1482 | 15269 | Same item quantity is not merging when creating Purchase Order from multiple Purchase Requisitions | Anshul Chandra | 6359222bd66d8108a123c4fe | 1.2.3.6.Q260112 | Highest | Reopen | Mohit sangwan | 712020:21fd6452-cd2e-4c89-a2d2-7ab3c0a5c6f8 |  | 2026-01-13 13:13 | 2026-01-19 14:44 | 2026-01-19 | Shivaizer
Bug | SHIV-1479 | 15232 | Global>>Incorrect delete confirmation message displayed and delete action not working in Customer Item Mapping | Somnath kumbhakar | 712020:6f36c619-c84c-4c7e-afa2-8d8976bdfd5e | 1.2.4.1.Q260117 | Medium | Reopen | Mohit sangwan | 712020:21fd6452-cd2e-4c89-a2d2-7ab3c0a5c6f8 |  | 2026-01-12 17:22 | 2026-01-19 15:01 | 2026-01-16 | Shivaizer
Bug | SHIV-1466 | 15120 | Same Item Quantity Is Not Merged in Purchase Requisition and Purchase Order | Anshul Chandra | 6359222bd66d8108a123c4fe | 1.2.3.6.Q260112 | High | Reopen | Piyush Khare | 712020:11da4d70-cd4a-4e49-9e06-a2be3affd318 |  | 2026-01-08 12:49 | 2026-01-19 15:50 | 2026-01-19 | Shivaizer
Bug | SHIV-1458 | 15013 | Asset MIS Report – Data Visibility & Allocation Issues | Mohit sangwan | 712020:21fd6452-cd2e-4c89-a2d2-7ab3c0a5c6f8 | 1.2.3.5.Q260111 | High | Reopen | Piyush Khare | 712020:11da4d70-cd4a-4e49-9e06-a2be3affd318 |  | 2026-01-05 18:55 | 2026-01-19 10:21 | 2026-01-19 | Shivaizer
Task | SHIV-1417 | 14519 | URGENT - GRN Screen – Header Display Order Correction, Field Rename & PO–Vendor Dependency Logic | Anshul Chandra | 6359222bd66d8108a123c4fe |  | Medium | To Do | Piyush Khare | 712020:11da4d70-cd4a-4e49-9e06-a2be3affd318 |  | 2025-12-20 13:32 | 2026-01-19 15:50 | 2026-01-16
Bug | SHIV-1391 | 14041 | Vendor Item Mapping View – Vendor Type, Vendor & Status values not displaying on View page | Kuldeep yadav | 712020:074b7522-30d5-4113-b52e-0df2956b5dbc |  | Medium | To Do | Piyush Khare | 712020:11da4d70-cd4a-4e49-9e06-a2be3affd318 |  | 2025-12-08 12:42 | 2026-01-15 12:53 | 2026-01-19 | Shivaizer
Task | SHIV-1279 | 13193 | Display the Total Pending Amount for the selected vendor while creating a Payment Voucher. | Anshul Chandra | 6359222bd66d8108a123c4fe |  | High | To Do | Piyush Khare | 712020:11da4d70-cd4a-4e49-9e06-a2be3affd318 |  | 2025-11-05 17:47 | 2026-01-19 15:49 | 2026-01-19
Bug | SHIV-1251 | 12987 | Term and Condition Master – Ref Source not showing in List and View | Anshul Chandra | 6359222bd66d8108a123c4fe |  | Medium | To Do | Piyush Khare | 712020:11da4d70-cd4a-4e49-9e06-a2be3affd318 |  | 2025-10-25 11:03 | 2026-01-14 19:37 | 2026-01-17 | Shivaizer