## Sheet1
Sr. No | Module | Change Request | Detailed requirement | Time Line (Working Days) | Front end resource man days | Back end resource man days | Status
1 | Agency Master | Remove "Not Available" option from Received option in Checklist Details of Agency Master module |  | check On points No 3 points here I mention
2 | Agreement Master | Kindly rename the Send mail toggle button as "Send Agreement expiry reminder mail". |  | check On points No 3 points here I mention
3 | Invoice Tracking Master/ Invoice Upload Master | "Payment Done" option should be present in the Actions field as well, the same should be allowed and accepted in Invoice Tracking Upload Master as well. |  | 1 |  | 1
4 | UI/UX | The order of the modules have been changed. Please keep the hierarchy as mentioned below in the same -Search tool -DNC Management -Settlement Tool -Settlement Tool -Settlement Approval -NDC Tool -Closure Module -NDC Tool -Revoke Closure -Vendor Management -Agency Search tool (To be renamed as Agency Master) -Agency Master (To be renamed as Agency Checker) -Agent Search tool(To be renamed as Agent Master) -Agent Master(To be renamed as Agent Checker) -Agreement Search tool(To be renamed as Agreement Master) -Agreement Master(To be renamed as Agreement Checker) -Invoice tracking search tool(To be renamed as Agreement Master) -Invoice tracking(To be renamed as Invoice tracking checker) -Show cause Notice -Masters -Upload Master data -Accounts Master -Customer Master -Allocation Master -Portfolio Master -Document Master -Trust Master -Regulatory notice master -Penalty charges master -Activity type master -Vendor checklist master -Upload document links -Admin Setup -Employee Master -Role Management -User master -Reports -Settlement Request report -Settlement Report -Settlement Schedule -Closure report -Revoke Closure report -NDC Report -Settlement V/S Collection report -Accounts without offer report -Broken Settlements Report -Post closure transaction report -Agency master report -Agency history report -Agent Master report -Agent history report -Agreement Master report -Agreement History report -Invoice tracking report -invoice tracking history report -show cause notice report -DNC Report -Access control matrix -Email delivery status |  | 1 | 1
` | Agent Master | On new agent creation and approval, agent id card no is created, but validation for ID Card End Date to be mandatory is not being provided based on the requirement mentioned in the FRD. |  | 0.5 |  | 0.5
| Code Merging |  |  | 3
| Ssl work | 17-Dec-2024: Full day allocated 27-Dec-2024: Full day allocated 28-Dec-2024: Half day allocated 30-12-2024 : Half day allocated 7th Jan 2024: 2-hour meeting 8th Jan 2024: 2.5 hours spent troubleshooting and identifying files not placed on the server 10th Jan 2024: 1-hour meeting |  | 3.5 |  | 3.5
| Stagging Patch |  |  | 2 |  |  | Approved
1 | Bureau data upload | 1. A new column “RARD OPS Closure date” is required in the final bureau reporting table. This column should capture the closure date from ndc_closure module for the account. Closure date in this table is already capturing the value date of the last payment made for an account.. 2. Valid values for the following columns is validated with actual values instead of codes. The validation should be code only to avoid issues with data discrepancies during upload · Gender · Address1 Category · Residence code · Address2 Category · Residence code · Account Type · Ownership indicator · Asset classification |  | 1 |  | 1 | Approved
2 | Testing and deployment |  |  | 0.5 |  | 0.5 | Approved
3 | Bureau Reporting | In case of closure, i.e. written off and settled status =99, then settlement_amount should be set to 0 or blank With testing and moviet upload | In case of closure, i.e. written off and settled status =99, then settlement_amount should be set to 0 or blank. | 0.5 |  | 0.5 | Approved
4 | Bureau Reporting | If the account is Live and it is not closed through closure module, then the written off and settled status =08 with testing and moviet upload | If the account is Live and it is not closed through closure module, then the written off and settled status =08 | 0.5 |  | 0.5 | Approved
| Bureau Reporting | The Overdue_amount and current_balance columns are currently giving negative values for the computation (TOS-LTD) |  | 0.5 |  | 0.5 | Approved
| Total |  |  | 14 | 1 | 8