## Sheet1
Module | Issue | Update/Query
Company Creation | Option to create a company has been removed | Resolve
Department Module | System requires Employee Name instead of allowing Department Head assignment | Resolve
Department Module | Submitted employee names did not appear under the selected departments
User Master | Password reset functionality | Resolved
Status Field | Unable to test functionality | Resolved
Vendor Master – Bulk Upload | Feature not tested due to existing vendor entries | Resolved
Item Specification | Manual entry for specifications not supported
Item Specification | Specification Head functionality not working
Vendor Column Testing | Emails sent from support@shivit.in instead of custom email ID | SMTP setting Required
Vendor Column Testing | No indication in RFQ that indent has already been mailed | In Process
Material Requisition | Database-related issue during submission | Resolved
Asset Management Module | Module pending | Bulk Upload resolved